## Week Wise Plan
Track#1a - Use Case & Presentation Layer Focused
20th Apr - 24th Apr | [6 empty] | Week Target WL Reports - 30% - Incoming WL Vol Main Dashboard(Patient, Sample, Test) - Drill Down Report for Daily & Hourly for Patient
TaskID | Task Description | Days | Start Date | End Date | Owner | % Completion
SD_W1_1 | Load Test Dictionary files for WorkLoad Reports | 1 day | 2015-04-20 | 2015-04-20 | Sanjay
SD_W1_2 | Data Mapper - LLD | 2 days | 2015-04-17 08:00 | 2015-04-20 17:00 | Sanjay
SD_W1_3 | Data Mapper - Coding | 2 days | 2015-04-21 08:00 | 2015-04-22 17:00 | Sanjay
SD_W_4 | Data Aggregator - LLD | 2 days | 2015-04-23 08:00 | 2015-04-24 17:00 | Sanjay
AK_W1_1 | Processed Schema | 1 day | 2015-04-17 08:00 | 2015-04-17 17:00 | Anup
AK_W1_2 | Tableau Server Configuration & Management | 2 days | 2015-04-20 08:00 | 2015-04-21 17:00 | Anup
AK_W1_3 | Incoming WL Vol Main Dashboard | 1 day | 2015-04-22 08:00 | 2015-04-22 17:00 | Anup
AK_W1_4 | Drill Down - Patient(Daily & Hourly) and Sample(Daily) | 2 days | 2015-04-23 08:00 | 2015-04-24 17:00 | Anup
EM_W1_1 | TDE File Implementation R&D | 2 days | 2015-04-17 08:00 | 2015-04-20 17:00 | Esha
EM_W1_2 | LIS File Corresponding to MW Data File | 2 days | 2015-04-21 08:00 | 2015-04-22 17:00 | Esha
EM_W1_3 | Landing Page for WL & TAT Reports | 3 days | 2015-04-23 08:00 | 2015-04-27 17:00 | Esha
RS_W1_1 | Development Environment Setup at onsite for showing reports | 1 day | 2015-04-20 08:00 | 2015-04-20 17:00 | Rajat
RS_W1_2 | Acceptance Test Cases for WL Reports | 2 days | 2015-04-21 08:00 | 2015-04-22 17:00 | Rajat
RS_W1_3 | Acceptance Test Cases for TAT Reports | 2 days | 2015-04-23 08:00 | 2015-04-24 17:00 | Rajat
RS_W1_4 | MW Data File Queries Resolution & Business Logic | 2 days | 2015-04-23 08:00 | 2015-04-24 17:00 | Rajat

## Anup
Anup
Task ID | Task Description | Sub Tasks | Key Decision/Remarks | % Completion | Status
AK_W_1 | Processed Schema | Sub Task #1
Sub Task #2
Sub Task #3

## Sanjay
Sanjay
Task ID | Task Description | Sub Tasks | Key Decision/Remarks | % Completion | Status
SD_W_1 | Load Test Disctionary files for WorkLoad Reports | Sub Task #1
Sub Task #2
Sub Task #3

## Esha
Esha
Task ID | Task Description | Sub Tasks | Key Decision/Remarks | % Completion | Status
EM_W_1 | TDE File Implmentation R&D | Sub Task #1
Sub Task #2
Sub Task #3

## Rajat
Esha
Task ID | Task Description | Sub Tasks | Key Decision/Remarks | % Completion | Status
RS_W_1 | Development Environment Setup at onsite for showing reports | Sub Task #1
Sub Task #2
Sub Task #3

## Overall Plan - Track#1A
Pre-requisite | 5 days | 2015-04-06 08:00 | 2015-04-10 17:00 |  | % Completion
LIS Schema Definition | 1 day | 2015-04-06 08:00 | 2015-04-06 17:00
LIS Sample Files | 1 day | 2015-04-07 08:00 | 2015-04-07 17:00 | 3
Middleware Schema Definition | 1 day | 2015-04-08 08:00 | 2015-04-08 17:00 | 4
Middleware Access | 1 day | 2015-04-09 08:00 | 2015-04-09 17:00 | 5
Development Environment Setup On-Premise & Cloud | 5 days | 2015-04-06 08:00 | 2015-04-10 17:00
Development Environment & Tools Setup on each team member laptop | 5 days | 2015-04-06 08:00 | 2015-04-10 17:00
Development Environment Setup in HCL Office | 5 days | 2015-04-06 08:00 | 2015-04-10 17:00
SVN Setup & Connectivity from offshore & Onsite | 5 days | 2015-04-06 08:00 | 2015-04-10 17:00
VPN Setup and Connectivity with Offshore | 5 days | 2015-04-06 08:00 | 2015-04-10 17:00
Training & Overview of WSo2 Platform & Relevant Components used in AIP Platform | 5 days | 2015-04-06 08:00 | 2015-04-10 17:00
Track #1a - Use Case Implementation | 36 days | 2015-04-06 08:00 | 2015-05-25 17:00
Workload Use Case | 36 days | 2015-04-06 08:00 | 2015-05-25 17:00
Divide LIS file Data on Week basis | 0 days | 2015-04-15 08:00 | 2015-04-15 08:00 |  |  | Anup
Load Manually Samples LIS Data Workload Reports | 2 days | 2015-04-15 08:00 | 2015-04-16 17:00 |  |  | Sanjay
Load Test Dictionary files for Workload Reports | 2 days | 2015-04-17 08:00 | 2015-04-20 17:00 | 16 |  | Sanjay
Data Dictionary Schema - MySQL | 1 day | 2015-04-16 08:00 | 2015-04-16 17:00 | 15 |  | Anup
Processed Schema | 1 day | 2015-04-17 08:00 | 2015-04-17 17:00 | 18 |  | Anup
Other Schema - Error, Log, Audit, Lookups | 0 days | 2015-04-17 17:00 | 2015-04-17 17:00 | 19 |  | Anup
Tableau Server Configuration & Management | 2 days | 2015-04-20 08:00 | 2015-04-21 17:00 | 20 |  | Anup
Data Mapper - LLD | 2 days | 2015-04-17 08:00 | 2015-04-20 17:00 | 16 |  | Sanjay
Data Mapper - Coding | 2 days | 2015-04-21 08:00 | 2015-04-22 17:00 | 22 |  | Sanjay
Data Aggregator - LLD | 2 days | 2015-04-23 08:00 | 2015-04-24 17:00 | 23 |  | Sanjay
Data Aggregator - Coding | 2 days | 2015-04-27 08:00 | 2015-04-28 17:00 | 24 |  | Sanjay
Data Validator - LLD | 0 days | 2015-04-28 17:00 | 2015-04-28 17:00 | 25 |  | Sanjay
Data Validator - Coding | 0 days | 2015-04-06 08:00 | 2015-04-06 08:00
Incoming WL Vol Main Dashboard | 1 day | 2015-04-22 08:00 | 2015-04-22 17:00 | 21 |  | Anup
Drill Down - Patient(Daily & Hourly) and Sample(Daily) | 2 days | 2015-04-23 08:00 | 2015-04-24 17:00 | 28 |  | Anup
Drill Down - Sample(Hourly) | 1 day | 2015-05-08 08:00 | 2015-05-08 17:00 | 65
Drill Down - Test(Daily & Hourly) | 2 days | 2015-05-11 08:00 | 2015-05-12 17:00 | 30 |  | Anup
Incoming WL Distribution Main Dashboard | 2 days | 2015-05-13 08:00 | 2015-05-14 17:00 | 31 |  | Anup
Drill Down WL Distribution(Tests Per Patient, Sample Per Patient | 1 day | 2015-05-15 08:00 | 2015-05-15 17:00 | 32 |  | Anup
Drill Down WL Distribution(Tests Per Patient, Sample Per Patient, Tests Per Sample) | 1 day | 2015-05-18 08:00 | 2015-05-18 17:00 | 33 |  | Anup
Incoming WL Test Type Distribution Main Dashboard | 2 days | 2015-05-19 08:00 | 2015-05-20 17:00 | 34 |  | Anup
Drill Down Test Type Distribution Daily & Hourly | 3 days | 2015-05-21 08:00 | 2015-05-25 17:00 | 35 |  | Anup
TDE file understanding | 1 day | 2015-04-16 08:00 | 2015-04-16 17:00 |  |  | Esha
TDE File Implementation | 2 days | 2015-04-17 08:00 | 2015-04-20 17:00 | 37 |  | Esha
Main Dashboard and Launch Tableau WL & TAT Landing Page | 3 days | 2015-04-23 08:00 | 2015-04-27 17:00 | 51 |  | Esha
Multitanency Handling - LLD | 0 days | 2015-04-06 08:00 | 2015-04-06 08:00 |  |  | Sanjay
Multitanency Handling - Implementation | 0 days | 2015-04-06 08:00 | 2015-04-06 08:00 |  |  | Sanjay
Integration with Core Engine | 10 days | 2015-05-04 08:00 | 2015-05-15 17:00 | 39 |  | Esha
Onsite Development Environment Setup | 1 day | 2015-04-20 08:00 | 2015-04-20 17:00 |  |  | Rajat
Acceptance Test Cases for Workload | 2 days | 2015-04-21 08:00 | 2015-04-22 17:00 | 43 |  | Rajat
Testing & Validation of workload reports on daily basis | 10 days | 2015-04-27 08:00 | 2015-05-08 17:00 | 67 |  | Rajat
Functional Query Resolution & Coordinate with ADD Team | 10 days | 2015-04-27 08:00 | 2015-05-08 17:00 | 67 |  | Rajat
Deploy in ADD environment & Validation | 4 days | 2015-05-11 08:00 | 2015-05-14 17:00 | 46 |  | Rajat,Srikanth
TAT Use Case | 30 days | 2015-04-06 08:00 | 2015-05-15 17:00
Middleware File Preparation & TAT Functional Resolution | 2 days | 2015-04-20 08:00 | 2015-04-21 17:00 |  |  | Rajat
Multitanency Handling | 0 days | 2015-04-06 08:00 | 2015-04-06 08:00 |  |  | Sanjay
LIS File Corresponding to MW Data File | 2 days | 2015-04-21 08:00 | 2015-04-22 17:00 | 38 |  | Esha
Schema Changes - MySQL | 1 day | 2015-04-27 08:00 | 2015-04-27 17:00 | 29 |  | Anup
Schema Changes in Cassandra | 2 days | 2015-04-29 08:00 | 2015-04-30 17:00 | 26 |  | Sanjay
Upload TAT Samples Files - MW & LIS Manually in Cassandra | 1 day | 2015-04-29 08:00 | 2015-04-29 17:00 | 26 |  | Sanjay
Data Mapper Correlation of MW & LIS file - LLD | 2 days | 2015-04-30 08:00 | 2015-05-01 17:00 | 54 |  | Sanjay
Data Mapper - Coding | 5 days | 2015-05-04 08:00 | 2015-05-08 17:00 | 55 |  | Sanjay
Data Aggregator - LLD | 0 days | 2015-05-08 17:00 | 2015-05-08 17:00 | 56 |  | Sanjay
Data Aggregator - Coding | 0 days | 2015-05-08 17:00 | 2015-05-08 17:00 | 57 |  | Sanjay
Data Validation - LLD | 0 days | 2015-05-08 17:00 | 2015-05-08 17:00 | 58 |  | Sanjay
Data Validation - Coding | 0 days | 2015-05-08 17:00 | 2015-05-08 17:00 | 59 |  | Sanjay
Predictable Turnaround Time for Incoming Workload | 3 days | 2015-04-28 08:00 | 2015-04-30 17:00 | 52 |  | Anup
Daily TAT | 1 day | 2015-05-01 08:00 | 2015-05-01 17:00 | 61 |  | Anup
Hourly TAT | 1 day | 2015-05-04 08:00 | 2015-05-04 17:00 | 62 |  | Anup
Filtration | 2 days | 2015-05-05 08:00 | 2015-05-06 17:00 | 63 |  | Anup
Main Dashboard (Co-relation of main report, filtration and corresponding drill down report) + formatting | 1 day | 2015-05-07 08:00 | 2015-05-07 17:00 | 64 |  | Anup
Integration with Core Engine | 10 days | 2015-05-04 08:00 | 2015-05-15 17:00 |  |  | Esha
Acceptance Test Cases for TAT | 2 days | 2015-04-23 08:00 | 2015-04-24 17:00 | 44 |  | Rajat
Testing & Validation of TAT reports on daily basis | 10 days | 2015-04-27 08:00 | 2015-05-08 17:00 | 67 |  | Rajat
Functional Query Resolution & Coordinate with ADD Team | 10 days | 2015-04-27 08:00 | 2015-05-08 17:00 | 67 |  | Rajat
Deploy in ADD environment & Validation | 4 days | 2015-05-11 08:00 | 2015-05-14 17:00 | 69 |  | Rajat,Srikanth

## Targets
W#1 (20Apr-24Apr) | W#2 (27Apr - 01May) | W#3 (4May-8May) | W#4(11May - 15May)
WL - 35% | TAT - 75% | TAT - 100% & WL - 50% | TAT - 100% & WL - 75% + Core Engine Integraiton
WL - Incoming Vol Dashboard | TAT - Predictable TAT | TAT - Hourly TAT report | WL - Vol. Distribution Main Dashboard
WL - Drill Down Patient | TAT - Daily TAT | WL - Drill Down Sample & Test | WL - Drill Down Vol. Distribution
Core Engine Integration