## Week Wise Plan
Track#1b - Core Engine & Integration Focused
20th Apr - 24th Apr
TaskID | Task Description | Days | Start Date | End Date | % Completion | Owner
AS_W1_1 | LIS File Parser - Low Level Design & Develompent | 1 Days | 2015-04-20 | 2015-04-20 17:00 |  | Abhishek
AS_W1_2 | LIS File Parser - Coding + UT [ Basic Skleton + Handles happy senario][75%] | 3 Days | 2015-04-21 08:00 | 2015-04-23 17:00 |  | Abhishek
SP_W1_1 | Middleware ODBC Connector - LLD | 1 Day | 2015-04-20 08:00 | 2015-04-20 17:00 |  | Srikanth
SP_W1_2 | Middleware ODBC Connector - Coding + UT | 4 Days | 2015-04-21 08:00 | 2015-04-24 17:00 |  | Srikanth
NG_W1_1 | Data Validator - LLD | 1 Day | 2015-04-20 08:00 | 2015-04-20 17:00 |  | Neha
NG_W1_2 | Data Validator - Coding + UT [Skleton + 1-2 validations] | 2 Days | 2015-04-21 08:00 | 2015-04-22 17:00 |  | Neha
NG_W1_3 | Data Access APIs - PostgreSQL LLD [66%] | 2 Days | 2015-04-23 08:00 | 2015-04-24 08:00 |  | Neha
KS_W1_1 | Schedular - LLD | 3 days | 2015-04-20 08:00 | 2015-04-22 17:00 |  | Kuntala
KS_W1_2 | Schedular - Coding [66%] | 2 days | 2015-04-23 08:00 | 2015-04-24 17:00 |  | Kuntala
| WSo2 Knowledge Sharing Session & Discussions | 3 days | 2015-04-21 08:00 | 2015-04-23 08:00 |  | Entire Team

## Abhishek
Abhishek
Task ID | Task Description | Sub Tasks | Key Decision/Remarks | % Completion | Status
AS_W1_1 | LIS File Parser - Low Level Design & Develompent | Sub Task #1
Sub Task #2
Sub Task #3

## Srikanth
Srikanth
Task ID | Task Description | Sub Tasks | Key Decision/Remarks | % Completion | Status
SP_W1_1 | Middleware ODBC Connector - LLD | Sub Task #1
Sub Task #2
Sub Task #3

## Neha
Neha
Task ID | Task Description | Sub Tasks | Key Decision/Remarks | % Completion | Status
NG_W1_1 | Data Validator - LLD | Sub Task #1
Sub Task #2
Sub Task #3

## Kuntala
Kuntala
Task ID | Task Description | Sub Tasks | Key Decision/Remarks | % Completion | Status
RS_W_1 | Development Environment Setup at onsite for showing reports | Sub Task #1
Sub Task #2
Sub Task #3

## Overall Plan - Track#1B
Track #1b - Core Engine & Integration Focused | 23 days | 2015-04-20 08:00 | 2015-05-20 17:00 |  | % Completion
Site Core Framework | 23 days | 2015-04-20 08:00 | 2015-05-20 17:00
LIS File Parser - Low Level Design | 1 day | 2015-04-20 08:00 | 2015-04-20 17:00 | Abhishek
LIS File Parser - Coding + UT [ Basic Skleton + Handles happy senario] | 4 days | 2015-04-21 08:00 | 2015-04-24 17:00 | Abhishek
Middleware ODBC Connector - LLD | 1 day | 2015-04-20 08:00 | 2015-04-20 17:00 | Srikanth
Middleware ODBC Connector - Coding + UT | 4 days | 2015-04-21 08:00 | 2015-04-24 17:00 | Srikanth
Data Validator - LLD | 1 day | 2015-04-20 08:00 | 2015-04-20 17:00 | Neha
Data Validator - Coding + UT [Skleton + 1-2 validations] | 2 days | 2015-04-21 08:00 | 2015-04-22 17:00 | Neha
Data Scrubber - LLD | 2 days | 2015-04-27 08:00 | 2015-04-28 17:00 | Abhishek
Data Scrubber - Coding + UT[Skleton + 1-2 fields] | 4 days | 2015-04-29 08:00 | 2015-05-04 17:00 | Abhishek
Data Access APIs - PostgreSQL LLD | 3 days | 2015-04-23 08:00 | 2015-04-27 17:00 | Neha
Data Access APIs - Coding + UT | 5 days | 2015-04-28 08:00 | 2015-05-04 17:00 | Neha
Schedular - LLD | 3 days | 2015-04-20 08:00 | 2015-04-22 17:00 | Kuntala
Schedular - Coding | 3 days | 2015-04-23 08:00 | 2015-04-27 17:00 | Kuntala
Batch Upload - LLD | 2 days | 2015-04-28 08:00 | 2015-04-29 17:00 | Kuntala
Batch Upload - Coding + UT [ WL + Happy Scenario] | 2 days | 2015-04-30 08:00 | 2015-05-01 17:00 | Kuntala
Data Transfer - LLD | 2 days | 2015-04-27 08:00 | 2015-04-28 17:00 | Srikanth
Data Transfer - Coding + UT [Skleton + Happy Scenario] | 3 days | 2015-04-29 08:00 | 2015-05-01 17:00 | Srikanth
Integration Defect Fixing | 8 days | 2015-05-11 08:00 | 2015-05-20 17:00 | Srikanth,Abhishek,Neha,Kuntala
Cloud Core Framework | 13 days | 2015-05-04 08:00 | 2015-05-20 17:00
Data Receiver - LLD | 2 days | 2015-05-04 08:00 | 2015-05-05 17:00 | Kuntala
Data Receiver - Coding + UT | 5 days | 2015-05-06 08:00 | 2015-05-12 17:00 | Kuntala
MB Queue Listner - LLD | 2 days | 2015-05-04 08:00 | 2015-05-05 17:00 | Srikanth
MB Queue Listner - Coding + UT | 4 days | 2015-05-06 08:00 | 2015-05-11 17:00 | Srikanth
CEP Configuration & Custom Logic | 3 days | 2015-05-05 08:00 | 2015-05-07 17:00 | Abhishek
BAM Configuration + Custom Logic | 3 days | 2015-05-08 08:00 | 2015-05-12 17:00 | Abhishek
DSS Configuration + Custom Logic | 2 days | 2015-05-05 08:00 | 2015-05-06 17:00 | Neha
ESB Composition & Aggregation | 4 days | 2015-05-07 08:00 | 2015-05-12 17:00 | Neha
Integration Defect Fixing | 8 days | 2015-05-11 08:00 | 2015-05-20 17:00 | Srikanth,Abhishek,Neha,Kuntala

## Targets
W#1 (20Apr-24Apr) | W#2 (27Apr - 01May) | W#3 (4May-8May) | W#4(11May - 15May) | W#4(17May - 22May) | W#4(25May - 25May)